## Sheet1
WEEK 1: Roald Dahl Poetry & Novel Website Requirements
Requirements | Author | % Completed | Notes | Team Comments | ID
Accessibility | Jack | 100% |  |  | Accessibility
Content Presentation | Thomas | 100% |  |  | Content-Presentation
Home Page Image Carousel | Marlie | 100% |  |  | Home-Page-Image-Carousel
Site Navigation | Afi | 0%
WEEK 3: Roald Dahl User Stories
User Story | Author | Completed | Corresponding Requirement | Notes | ID
Labeling Poems & Quotes | Jack | 100% | Content Presentation |  | User-Stories:-Poems-and-Quotes
Sections with documented quotes | Jack | 100% | Content Presentation |  | User-Stories:-Poems-and-Quotes
Commenting on Poems & Quotes | Jack | 100% | Site Navigation |  | User-Stories:-Poems-and-Quotes
Sorting Poems & Quotes | Jack | 100% | Content Presentation |  | User-Stories:-Poems-and-Quotes
View Accomplishments | Thomas | 100% | Content Presentation |  | User-Stories:-Learn-About-Roald-Dahl
Watch Clips | Thomas | 100% | Accessibility |  | User-Stories:-Learn-About-Roald-Dahl
View Portraits/Photos | Thomas | 100% | Accessibility, Home Page Image Carousel |  | User-Stories:-Learn-About-Roald-Dahl
Purchase Samples | Thomas | 100% | Site Navigation, Content Presentation |  | User-Stories:-Learn-About-Roald-Dahl
Pinning Photos on Pinterest | Marlie | 100% | Site Navigation, Content Presentation |  | User-Story:-Pinning-Roald-Dahl-Photos-and-Images-on-Pinterest
Sharing Poems on FB | Marlie | 100% | Site Navigation, Content Presentation |  | User-Story:-Sharing-Roald-Dahl-Poems-on-Facebook
Sharing Page on FB | Marlie | 100% | Site Navigation, Content Presentation |  | User-Story:-Sharing-the-PDG-for-RDF-Webpage-on-Facebook
Sharing Page on Twitter | Marlie | 100% | Site Navigation, Content Presentation |  | User-Story:-Sharing-the-PDG-for-RDF-Webpage-on-Twitter
News Feed Story 1 | Afi | 0%
News Feed Story 2 | Afi | 0%
News Feed Story 3 | Afi | 0%
News Feed Story 4 | Afi | 0%
WEEK 3: User Story Size Estimations (scale: 1,2,3,5,8,16)
User Story | Marlie | Jack | Thomas | Afi | Team Consensus | % Complete
Labeling Poems & Quotes | 3 | 3 |  |  |  | 50%
Sections with documented quotes | 2 | 3 |  |  |  | 50%
Commenting on Poems & Quotes | 3 | 2 |  |  |  | 50%
Sorting Poems & Quotes | 2 | 3 |  |  |  | 50%
View Accomplishments | 2 |  | 2 |  |  | 50%
Watch Clips | 3 |  | 2 |  |  | 50%
View Portraits/Photos | 2 |  | 3 |  |  | 50%
Purchase Samples | 2 |  | 2 |  |  | 50%
Pinning Photos on Pinterest | 2 |  |  |  |  | 25%
Sharing Poems on FB | 2 |  |  |  |  | 25%
Sharing Page on FB | 3 |  |  |  |  | 25%
Sharing Page on Twitter | 3 |  |  |  |  | 25%
News Feed Story 1 | [5 empty] | 0%
News Feed Story 2 | [5 empty] | 0%
News Feed Story 3 | [5 empty] | 0%
News Feed Story 4 | [5 empty] | 0%
WEEK 4: Creating Issues & Populating the Sprint
Issues | Author | % Completed | Notes | Team Comments | ID
Create a Poem Page | Marlie | 100% | Created a separate page for RD poems and linked it to the home page. | Reviewed by Afi | https://github.com/suwebdev/sparkling-art/issues/3
Add Titles and Publish Dates to Poems | Marlie | 100% | Added two poems to the newly created poem page and included titles and published by dates. | Reviewed by Afi | https://github.com/suwebdev/sparkling-art/issues/4
TBD | Afi | 0%
TBD | Afi | 0%
TBD | Thomas | 0%
TBD | Thomas | 0%
TBD | Jack | 0%
TBD | Jack | 0%
WEEK 5: Working on Code
Issues | Author | % Completed | Notes | Team Comments | ID
Carousel Home Page | Marlie | 100% | Created a basic carousel with several RD images as a featured section on the home page. | Reviewed by Thomas | https://github.com/suwebdev/sparkling-art/issues/7
Poetry Site Logo | Marlie | 100% | Created a home page logo to add to the home page banner for site identification. | Reviewed by Thomas | https://github.com/suwebdev/sparkling-art/issues/8
TBD | Afi | 0%
TBD | Afi | 0%
TBD | Thomas | 0%
TBD | Thomas | 0%
Created Quotes Page | Jack | 98% |  | Created quotes page, needs to update Jack branch to be even with master. | https://github.com/suwebdev/sparkling-art/issues/10
Added Comments Section to Quotes Page | Jack | 98% |  | Added Comments section, needs to update Jack branch to be even with the Master. | https://github.com/suwebdev/sparkling-art/issues/11
WEEK 6: Pull Requests
Issues | Author | % Completed | Notes | Team Comments | ID
Pink Text | Marlie | 100% | Created pull request to make the home page text pink | asked for team review/discussion | https://github.com/suwebdev/sparkling-art/pull/18
Login or Sign In | Marlie | 100% | changed the sign in link to text "log on" to see how the group feels about the different word choices | asked for team review/discussion | https://github.com/suwebdev/sparkling-art/pull/19
TBD | Afi | 0%
TBD | Afi | 0%
TBD | Thomas | 0%
TBD | Thomas | 0%
TBD | Jack | 98%
TBD | Jack | 98%